## Tabelle1
Risk | Description | Prob. of Occurance | Damage | Mitigation Strategy | Person in Charge | Risk Factor (sorted)
time management | bad time estimation of certain tasks | 30-60% |  | improved scheduling | All | 0
Technical/logical complexity | problems during implementation of logic and technology | 60-90% |  | detailed planning | Bene | 1
Division of labour | disproportionate distribution of tasks | 5-30% |  | communication | Oli | 2
Deployment | Live-Server, Mail-Server, Data-Base-Server problems | 5-30% |  | preparation | Bene | 3
Code management | insufficient branching, lack of comments | 40-70% |  | peer coding/review | Oli | 4
Dissatisfaction | application not appealing to users (appearance, handling, ...) | 5-30% |  | tests, feedback | Mats | 5
project management | neglect of pm tasks | 5-40% |  | finish after lecture | Mats | 6
content | lack of content | 5-30% |  | feedback, brainstorming | All | 7