## Tabelle1
Risk | Description | Prob. of Occurance | Damage | Mitigation Strategy | Person in Charge | Risk Factor (sorted)
time management | bad time estimation of certain tasks | 40-80% | 9 | improved scheduling | All | 8
Technical/logical complexity | problems during implementation of logic and technology | 60-70% | 8 | detailed planning | Bene | 7
Division of labour | disproportionate distribution of tasks | 5-30% | 6 | communication | Oli | 6
Deployment | Live-Server, Mail-Server, Data-Base-Server problems | 5-30% | 5 | preparation | Bene | 5
Code management | insufficient branching, lack of comments | 40-70% | 4 | peer coding/review | Oli | 4
Dissatisfaction | application not appealing to users (appearance, handling, ...) | 5-30% | 4 | tests, feedback | Mats | 3
project management | neglect of pm tasks | 5-40% | 3 | finish after lecture | Mats | 2
content | lack of content | 5-30% | 1 | feedback, brainstorming | All | 1